## 00 How to use
Topic | Detail
Purpose | The complete pre-launch test plan for the Soulful Bhakti Android app. Work top to bottom: run the Release gate, then the Smoke suite, then every P0 row of the Test matrix, then the rest as time allows.
Cadence | Smoke suite on every build. Release gate + all P0 rows for every Play upload. Full matrix for a major release (new feature, SDK bump, targetSdk change).
Release gate rule | Do NOT publish while any P0 row is Fail or Blocked, and while any Smoke row is not Pass. A single unverified P0 blocks the launch.
Priority meaning | P0 = release blocker (money, auth, playback, privacy, install). P1 = critical path, must pass before launch. P2 = important, may ship with a logged known issue. P3 = polish.
Status meaning | Not run = untouched. Pass = verified on a device or by CI this cycle. Fail = broken, needs a fix. Blocked = could not test (say why in Evidence). N/A = not applicable to this build.
Evidence rule | Every Pass or Fail needs one artefact: a screenshot file name, the logcat snippet, the adb command output, or the GitHub Actions run URL. A tick with no evidence is not a test.
Layer meaning | Device = manual on a real phone or emulator. CI = proven by the pipeline (see the Automated sheet). Either = can be done both ways; CI is preferred.
Test accounts needed | 1) a Google account with a free plan (signed-in checks), 2) a Play licence-test account (purchase and restore), 3) an account with real listening history (Insights), 4) a second account for cross-account checks.
Builds needed | The release APK for sideload checks, and the AAB published to Play internal testing for the real signing/update path.
SIGN-OFF
Version / versionCode
Artifact SHA-256
Tester
Date
Smoke result (all Pass?)
P0 count: Fail / Blocked
Decision (SHIP / HOLD)

## 01 Release gate
Phase | Step | How / command | Expected | Status | Evidence / notes
0 Prepare | Code freeze and scope | Only release-blocking fixes land | No new features in the release branch | Not run
0 Prepare | Bump versionCode | pubspec version: 1.0.0+NN | Higher than the highest on Play | Not run
0 Prepare | Confirm the paid/free split is intended | GET /supabase/tracks and count status | The paid share matches the launch plan | Not run
1 Build | Push or merge to main | git push origin main | main is clean and matches the intended commit | Not run
1 Build | CI Flutter Verify | gh workflow run flutter-verify.yml -f test_path=test | Analyze count equals the baseline and every test passes | Not run
1 Build | Dispatch the release build | gh workflow run android-release.yml -f format=appbundle (and apk) | Build job green | Not run
1 Build | Keystore pinned to the Play upload key | Release step Verify the keystore is the Play upload key | SHA-256 matches the pinned value | Not run
1 Build | Required .env keys present | Release step Verify required .env keys | SUPABASE_URL, SUPABASE_ANON_KEY, CLERK_PUBLISHABLE_KEY, ONESIGNAL_APP_ID all set | Not run
1 Build | Drift schema guard + migrations | Release steps Verify drift schema snapshots / Verify database migrations | Both pass | Not run
1 Build | Version resolved from pubspec | Release step Resolve version | versionName/versionCode match pubspec | Not run
2 Artifact | Artifact carries the intended version | Release step Verify AAB | versionCode in the artifact equals the resolved one | Not run
2 Artifact | Artifact is signed | Release step Verify AAB signature | jarsigner reports a verified signature with the expected CN | Not run
2 Artifact | Permission audit | Release step Audit shipped permissions | AD_ID absent; the permission list is accounted for | Not run
2 Artifact | Secrets cleaned up | Release step Clean up secrets (always) | No keystore, key.properties or .env left in the workspace | Not run
2 Artifact | Record the SHA-256 | sha256sum on the downloaded artifact | Written into the release notes | Not run
3 Install | In-place update over the last build | adb install -r app-release.apk | Installs over the old version; data and session survive | Not run
3 Install | Cold start | Launch the app | Home within a few seconds; no crash | Not run
4 Gate | Run the Smoke suite | Sheet 02 | Every row Pass | Not run
4 Gate | Run every P0 row of the Test matrix | Sheet 03, filter Priority = P0 | No Fail and no Blocked | Not run
4 Gate | Playback gate matrix on device | Rows GAT-01 .. GAT-22 | Sign-in gate, paywall gate and stream endpoints all behave | Not run
4 Gate | Insights numbers vs real history | Rows ANA-01 .. ANA-15 | Cards, chart and deity card match the underlying plays | Not run
4 Gate | Push and deep link from the dashboard | Rows PSH-01 .. PSH-03 | Notification arrives and lands on the right screen | Not run
4 Gate | Purchase and restore | Rows PRM-01 .. PRM-05 with a licence-test account | Purchase unlocks, restore works, no charge on dismiss | Not run
5 Publish | Upload the AAB to internal testing | Play Console; internal testing track | Upload accepted; no policy warnings | Not run
5 Publish | Install from internal testing on a clean device | Play Store link; install | Installs and runs; Smoke suite again | Not run
5 Publish | Data safety and store listing still accurate | Play Console forms | No new permission or data collection to declare | Not run
5 Publish | Staged rollout | Start at the lowest percentage | Rollout live, not halted | Not run
6 After | Monitor for 24h | Crashlytics, Play vitals (ANR), support inbox | No new fatal cluster or ANR spike | Not run
6 After | Promote or halt | Play Console | Decision recorded here with the reason | Not run
6 After | Tag the release | git tag vNN and push | Tag points at the commit the artifact was built from | Not run

## 02 Smoke suite
ID | What to verify | How | Expected | Status | Evidence
SMK-01 | Installs over the previous build | adb install -r <apk> | Success; data and session preserved | Not run
SMK-02 | Cold start to Home | Launch | Home renders; no crash | Not run
SMK-03 | Signed-out play attempt is gated | Sign out; tap any track | Sign-in popup; no audio | Not run
SMK-04 | Google sign-in works | Continue with Google | Signed in; profile shows name and email | Not run
SMK-05 | A free track plays | Tap a free track | Audio audible; mini player and notification appear | Not run
SMK-06 | Notification transport | Pause and resume from the notification | Playback follows | Not run
SMK-07 | Next, previous and seek | Use the player controls | All three behave | Not run
SMK-08 | A paid track shows the paywall | Tap a paid track on the free plan | Superwall paywall appears; nothing plays | Not run
SMK-09 | Home shelves and deity chips | Scroll Home; tap a chip | Shelves render; the chip opens its shelf | Not run
SMK-10 | Search and play | Search a known title; play a result | Result plays | Not run
SMK-11 | Library write path | Like a track; create a playlist; add a track | All three persist after restart | Not run
SMK-12 | Lyrics render | Open the lyrics tab | Lyrics appear; synced highlight follows if available | Not run
SMK-13 | Insights opens and agrees | Insights; switch range; open Minutes | Numbers match the detail page | Not run
SMK-14 | Background playback | Home button; screen off for 2 minutes | Audio continues | Not run
SMK-15 | Network loss handling | Airplane mode mid-play | Pause with a message; no ANR | Not run
SMK-16 | Sign-out stops audio | Sign out while playing | Audio stops; queue clears | Not run
SMK-17 | About shows the built version | Settings; About | Matches the artifact versionCode | Not run
SMK-18 | Profile plan and upgrade | Profile; Upgrade to Pro Plan Now | Paywall opens | Not run

## 03 Test matrix
ID | Area | Test case | Preconditions | Steps | Expected result | Priority | Layer | Status | Device / build | Evidence | Notes
INS-01 | A · Install & update | Fresh install on a clean device | Device with the app uninstalled | adb install -r SoulfulBhakti-vNN.apk; launch | App reaches Home; no crash; About shows the artifact versionCode | P0 | Device | Not run
INS-02 | A · Install & update | In-place update over the previous build | Previous versionCode installed and used (history, playlists, likes) | adb install -r (higher versionCode); launch | Update succeeds without uninstall; history, playlists, likes and the Clerk session survive | P0 | Device | Not run
INS-03 | A · Install & update | Update over the Play-installed build | Play build installed from internal testing | Publish a higher versionCode to internal testing and update | Play accepts the upload; the app updates in place; no signature mismatch | P0 | Device | Not run
INS-04 | A · Install & update | Upload-key APK cannot replace a Play build | Play build installed | adb install -r the upload-key APK | INSTALL_FAILED_UPDATE_INCOMPATIBLE is expected; document it as intended, not a bug | P2 | Device | Not run
INS-05 | A · Install & update | versionCode strictly increases | Previous release published | Compare pubspec version with the Play track | versionCode is greater than the last uploaded one; About shows the same number as the artifact | P0 | CI | Not run
INS-06 | A · Install & update | Only the intended ABIs ship | Release artifact in hand | Inspect the APK lib folders | arm64-v8a and armeabi-v7a only; no x86/x86_64 payload | P1 | CI | Not run
INS-07 | A · Install & update | Unreadable-data upgrade | App with data from a build two or more versions old | Update directly to the current build; launch | Drift migrates the schema; no crash; history still readable on the Analytics screen | P0 | Device | Not run
INS-08 | A · Install & update | Uninstall and reinstall | App installed | Uninstall; install again; launch | Starts clean with the splash, no stale state, signed out | P1 | Device | Not run
INS-09 | A · Install & update | First launch after install needs no permission grant | Fresh install | Launch and use Home for 30s | No runtime permission dialog at launch; nothing blocks use | P1 | Device | Not run
STA-01 | B · Startup & splash | Cold start shows the splash, then Home | App force-stopped | Launch; watch the first two seconds | Splash is visible for at least ~1.2s and cross-fades to Home; no white flash or black frame | P1 | Device | Not run
STA-02 | B · Startup & splash | Splash never hangs | App force-stopped, network unavailable | Disable network; launch; wait 30s | Home appears within ~8s with its own error/empty states; never stuck on the splash | P0 | Device | Not run
STA-03 | B · Startup & splash | Cold start in airplane mode | Airplane mode on | Launch and browse Home, Search, Library | App opens; cached content renders; network-dependent parts show errors, not a crash | P1 | Device | Not run
STA-04 | B · Startup & splash | First launch while signed out cannot play | Signed out, cold start | Tap a track within the first seconds | Sign-in popup appears; no audio starts; no silent 401 in the logs | P0 | Device | Not run
STA-05 | B · Startup & splash | Warm start from Recents restores state | Playing a track | Home; reopen from Recents | Same screen, same queue, same track and position; playback uninterrupted | P1 | Device | Not run
STA-06 | B · Startup & splash | Process death mid-playback | Playing, signed in | Kill the process from Recents; relaunch | Queue and track restored at the saved position, paused, not auto-playing | P2 | Device | Not run
STA-07 | B · Startup & splash | Crash-free startup | Crashlytics available | Cold start 3x on two devices | No new fatal or non-fatal entries attributable to startup | P0 | Either | Not run
STA-08 | B · Startup & splash | Startup time | Mid-range device | Cold start with a stopwatch or logcat timestamps | First frame well under 3s warm, and Home usable within ~5s cold | P2 | Device | Not run
AUT-01 | C · Authentication (Clerk / Google) | Signed out browsing is unrestricted | Signed out | Open Home, Search, Library, an album, a playlist | Everything browses normally; no login wall | P0 | Device | Not run
AUT-02 | C · Authentication (Clerk / Google) | Sign-in popup appears on a play attempt | Signed out | Tap a free track from a track row | The Google sign-in dialog opens; playback does not start | P0 | Device | Not run
AUT-03 | C · Authentication (Clerk / Google) | Dismissing the popup changes nothing | Signed out, popup open | Back out of the dialog | No audio, no queue change, no error toast | P0 | Device | Not run
AUT-04 | C · Authentication (Clerk / Google) | Google sign-in succeeds | Signed out | Continue with Google; pick an account | Dialog closes; profile shows the name and email; subscription row shown | P0 | Device | Not run
AUT-05 | C · Authentication (Clerk / Google) | Session survives restart | Signed in | Force-stop; launch | Still signed in; profile still shows the account | P0 | Device | Not run
AUT-06 | C · Authentication (Clerk / Google) | Sign-out stops playback and clears the queue | Signed in, playing a track | Profile; Sign Out; confirm | Audio stops immediately; mini player clears; queue emptied; profile shows signed out | P0 | Device | Not run
AUT-07 | C · Authentication (Clerk / Google) | Sign-out failure keeps the session | Signed in, native sign-out fails | Trigger sign-out while the call fails | Dialog stays open with an inline error; the user remains signed in | P2 | Device | Not run
AUT-08 | C · Authentication (Clerk / Google) | Cancelling the Google chooser | Signed out, popup open | Continue with Google, then BACK out of the chooser | Dialog closes cleanly with no error message | P1 | Device | Not run
AUT-09 | C · Authentication (Clerk / Google) | Clerk unavailable | Clerk Native API disabled or unreachable | Open the sign-in popup and wait | Temporarily unavailable message with Try again; no endless spinner | P1 | Device | Not run
AUT-10 | C · Authentication (Clerk / Google) | Auth state resolves before playback is gated | Signed in, fresh launch | Tap a free track within the first seconds of Home | Plays; no spurious sign-in popup (regression guard for the v96 mirror fix) | P0 | Device | Not run
AUT-11 | C · Authentication (Clerk / Google) | Account deletion | Signed in with local data | Profile; Delete Account; confirm | Clerk account deleted; local playlists, likes and history cleared; signed out; analytics identity reset | P0 | Device | Not run
AUT-12 | C · Authentication (Clerk / Google) | Second account on the same device | Signed in as A with local data; sign out; sign in as B | Repeat the sign-out and sign-in flow | No cross-account leakage of playlists, likes or referral binding | P1 | Device | Not run
AUT-13 | C · Authentication (Clerk / Google) | Offline sign-in attempt | Airplane mode | Try Continue with Google | Clear failure message; app remains usable signed out; no crash | P2 | Device | Not run
AUT-14 | C · Authentication (Clerk / Google) | Push identity follows the session | Signed in | Check OneSignal identity after login and after logout | login sets the external id; logout reverts to a device-scoped user | P2 | Either | Not run
GAT-01 | D · Playback gate (login + paywall) | Signed out · free track from a track row | Signed out | Tap a free track row | Sign-in popup; no playback | P0 | Device | Not run
GAT-02 | D · Playback gate (login + paywall) | Signed out · free track from a home card | Signed out | Tap a track card on Home (cover or play control) | Sign-in popup; no playback | P0 | Device | Not run
GAT-03 | D · Playback gate (login + paywall) | Signed out · album or playlist card play button | Signed out | Tap the play control on an album/playlist card | Sign-in popup; no playback, no remote/device dialog | P0 | Device | Not run
GAT-04 | D · Playback gate (login + paywall) | Signed out · artist top-tracks play | Signed out | Open an artist; tap the section play control | Sign-in popup | P1 | Device | Not run
GAT-05 | D · Playback gate (login + paywall) | Signed out · specials carousel Play Now | Signed out | Tap Play Now on the featured banner | Sign-in popup; the shelf screen does not open onto a dead queue | P1 | Device | Not run
GAT-06 | D · Playback gate (login + paywall) | Signed out · liked-songs card play | Signed out, likes exist locally | Tap play on the Liked Tracks card | Sign-in popup | P1 | Device | Not run
GAT-07 | D · Playback gate (login + paywall) | Signed out · Start radio from track options | Signed out | Track options; Start Radio | Sign-in popup; no radio queue is built | P2 | Device | Not run
GAT-08 | D · Playback gate (login + paywall) | Signed out · album page Play and Shuffle | Signed out | Open an album; tap Play, then Shuffle | Sign-in popup on both; nothing plays | P0 | Device | Not run
GAT-09 | D · Playback gate (login + paywall) | Signed in · free track plays everywhere | Signed in, free plan | Tap a free track from a row, a card, an album, the artist section and Search | Every surface starts playback immediately with no extra dialog | P0 | Device | Not run
GAT-10 | D · Playback gate (login + paywall) | Signed in · paid track shows the paywall | Signed in, free plan | Tap a paid track (e.g. from a fully paid album) | Superwall paywall appears; playback does not start | P0 | Device | Not run
GAT-11 | D · Playback gate (login + paywall) | Premium · paid track plays | Signed in with an active subscription | Tap a paid track | Plays immediately; no paywall | P0 | Device | Not run
GAT-12 | D · Playback gate (login + paywall) | Signed out · paid track, order of gates | Signed out | Tap a paid track; sign in when asked | Sign-in popup FIRST, then the paywall; never the paywall before sign-in | P0 | Device | Not run
GAT-13 | D · Playback gate (login + paywall) | Paid album cascades to its tracks | Signed in, free plan | Open a paid album and tap a track whose own status is free | Row shows the padlock and the tap opens the paywall | P0 | Device | Not run
GAT-14 | D · Playback gate (login + paywall) | Stream endpoint: signed out | Signed out | HEAD /stream/<free track id> on the app local server | 401 Unauthorized; no audio bytes | P0 | Either | Not run
GAT-15 | D · Playback gate (login + paywall) | Stream endpoint: signed in | Signed in | HEAD then GET /stream/<free track id> | 200 with audio/ogg and a content-length; full body retrievable | P0 | Either | Not run
GAT-16 | D · Playback gate (login + paywall) | Stream endpoint: paid track, non-premium | Signed in, free plan | HEAD /stream/<paid track id> | 403 Forbidden | P0 | Either | Not run
GAT-17 | D · Playback gate (login + paywall) | Stream endpoint: unknown track | Signed in | HEAD /stream/<nonexistent id> | 404, not 401 (a bad id must not read as a login problem) | P2 | Either | Not run
GAT-18 | D · Playback gate (login + paywall) | Saved queue is not restored when signed out | Queue saved from a signed-in session; sign out; relaunch | Launch and check the mini player | Queue is empty; no unplayable queue is presented | P1 | Device | Not run
GAT-19 | D · Playback gate (login + paywall) | Sign-out during playback | Playing | Sign out mid-track | Audio stops within a second; the notification clears | P0 | Device | Not run
GAT-20 | D · Playback gate (login + paywall) | No prefetch while signed out | Signed out | Scroll Home for 30s; watch the network log | No audio byte prefetch requests are issued | P2 | Either | Not run
GAT-21 | D · Playback gate (login + paywall) | Locked row affordances | Signed in, free plan | Look at the paid album rows | Padlock shown, no play/pause icon, row cannot appear as the active track | P1 | Device | Not run
GAT-22 | D · Playback gate (login + paywall) | Queue actions while signed out | Signed out | Track options; Add to Queue; then press play | Either the action is gated by the sign-in popup, or playback is gated with a clear prompt; never a silent failure | P1 | Device | Not run
PLY-01 | E · Playback core | Play, pause and resume | Signed in | Tap a free track; pause; resume | Audio and the mini player agree at every step; the notification follows | P0 | Device | Not run
PLY-02 | E · Playback core | Seek within a track | Playing | Drag the timeline to 25%, 50%, 90% | Playback jumps to the position; the bar and the elapsed time agree; no desync | P0 | Device | Not run
PLY-03 | E · Playback core | Seek while buffering | Weak network | Start a track and seek immediately | Seek is honoured once buffered; no stuck spinner or silence forever | P1 | Device | Not run
PLY-04 | E · Playback core | Next and previous | Playing, queue of 5+ | Press next to the last track; press previous to the first | Boundaries behave per the loop mode; no crash and no empty index | P0 | Device | Not run
PLY-05 | E · Playback core | Autoplay the next track | Playing, queue of 3+ | Let a track finish | The next track starts automatically; the mini player and notification update | P0 | Device | Not run
PLY-06 | E · Playback core | End of the queue | Playing, loop off | Let the last track finish | Playback stops cleanly and stays at the end; no error surface | P1 | Device | Not run
PLY-07 | E · Playback core | Shuffle on and off | Playing, queue of 5+ | Toggle shuffle twice | Order changes and restores; the active track is not lost; the icon state matches | P1 | Device | Not run
PLY-08 | E · Playback core | Repeat none, all, one | Playing | Cycle the loop modes through a full track | Behaviour matches each mode exactly | P1 | Device | Not run
PLY-09 | E · Playback core | Add to queue and play next | Playing, queue non-empty | Track options; Add to Queue; Play Next | The queue order matches the action; playback is interrupted only where intended | P1 | Device | Not run
PLY-10 | E · Playback core | Remove and reorder the queue | Queue of 5+ | Queue page; remove a middle track; reorder two tracks | The engine queue and the UI agree; the current track keeps playing | P1 | Device | Not run
PLY-11 | E · Playback core | Jump to a queued track | Queue of 5+ | Tap a different track in the queue | Jumps and plays; the index and mini player stay in sync | P1 | Device | Not run
PLY-12 | E · Playback core | Gapless transition | Playing near the end of a track | Let a track roll into the next | No audible gap or double-start; seekbar and artwork switch once | P2 | Device | Not run
PLY-13 | E · Playback core | Rapid next spam | Playing | Tap next 10x quickly | App stays responsive; ends on a valid track; no duplicated entries | P2 | Device | Not run
PLY-14 | E · Playback core | Play the same track twice | Playing track X | Tap X again from the list | No duplicate row; behaves as restart/unpause per design; no crash | P2 | Device | Not run
PLY-15 | E · Playback core | Sleep timer | Playing | Settings; sleep timer; choose the shortest option | Playback pauses at the end of the timer; the timer can be cancelled before it fires | P2 | Device | Not run
PLY-16 | E · Playback core | Endless playback append | Playing the last track with endless mode on | Let the last track end | Similar tracks are appended and the queue keeps going; nothing duplicates | P2 | Device | Not run
PLY-17 | E · Playback core | Karaoke toggle | A track with a karaoke file | Player; switch Original/Karaoke | Karaoke variant plays, the position is preserved, the switch flips back cleanly | P1 | Device | Not run
PLY-18 | E · Playback core | Track without a karaoke file | A track with no karaoke path | Open the player | The Original/Karaoke control is not shown | P3 | Device | Not run
PLY-19 | E · Playback core | Very long track | A track over 60 minutes | Seek to 95% and let it finish | Position handles hours; no overflow in the timeline labels | P3 | Device | Not run
PLY-20 | E · Playback core | Broken or missing audio object | A track whose storage path is wrong | Play it | A clear failure; the app does not crash; the next track still plays | P1 | Either | Not run
PLY-21 | E · Playback core | Volume and normalization | Playing | Change volume; toggle audio normalization in Settings | Volume responds; the toggle persists and does not restart playback | P3 | Device | Not run
PLY-22 | E · Playback core | Playback position persistence | Playing track X at ~40% | Switch to another track and back | Position policy matches the design; no reset loop or double restore | P2 | Device | Not run
AND-01 | F · Android integration | Background playback | Playing | Press Home and lock the screen | Audio continues; the foreground notification stays; no battery-killer stall | P0 | Device | Not run
AND-02 | F · Android integration | Media notification controls | Playing | Use play, pause, next, previous and seek on the notification | The app state follows every action and the notification artwork/title is correct | P0 | Device | Not run
AND-03 | F · Android integration | Lock-screen controls | Playing, screen locked | Use the lock-screen media controls | Same as the notification; no unlock required | P1 | Device | Not run
AND-04 | F · Android integration | Bluetooth headset buttons | Bluetooth headset connected, playing | Press play/pause and next on the headset | Actions reach the app; audio and UI agree | P1 | Device | Not run
AND-05 | F · Android integration | Wired headset unplug | Wired headset, playing | Unplug the headset | Playback pauses (audio focus loss) as designed | P2 | Device | Not run
AND-06 | F · Android integration | Incoming call during playback | Playing | Receive a call; hang up | Audio pauses for the call and resumes after, or stays paused per focus rules, without a crash | P1 | Device | Not run
AND-07 | F · Android integration | Audio focus with another music app | Playing | Start playback in another music app | This app pauses; returning to it resumes cleanly | P1 | Device | Not run
AND-08 | F · Android integration | Notification permission prompt | Android 13+, signed out | Sign in | The permission prompt is requested after sign-in, not at launch; the choice is respected | P1 | Device | Not run
AND-09 | F · Android integration | Home-screen widget | Widget added to the launcher | Play from the app, then look at the widget | Widget shows the current track and controls respond | P2 | Device | Not run
AND-10 | F · Android integration | Set as ringtone | A track eligible for ringtone | Player; ringtone action | Ringtone is written and applied, or a clear failure message is shown | P2 | Device | Not run
AND-11 | F · Android integration | OEM battery optimisation | Xiaomi/Redmi and one other OEM | Play for 10 minutes with the screen off | Playback is not killed; document autostart guidance if it is | P1 | Device | Not run
AND-12 | F · Android integration | In-app messages do not cover the player | Playing | Trigger an in-app message from the dashboard | Messages are suppressed while audio plays and show when it is paused | P3 | Device | Not run
AND-13 | F · Android integration | Rotation and multi-window | Playing | Rotate; enter split screen | Layout adapts; playback continues; no overflow exceptions | P2 | Device | Not run
NET-01 | G · Streaming & network | Wi-Fi to mobile data mid-track | Playing on Wi-Fi | Turn Wi-Fi off | Playback continues or rebuffers briefly; no crash and no 401/403 | P1 | Device | Not run
NET-02 | G · Streaming & network | Airplane mode mid-play | Playing | Enable airplane mode | Playback pauses with a toast; no ANR; recovering the network resumes | P0 | Device | Not run
NET-03 | G · Streaming & network | Recovery after the network returns | Offline, paused | Restore the network; press play | Resumes without relaunching the app | P1 | Device | Not run
NET-04 | G · Streaming & network | Slow network | Throttled to ~2G | Start a track and seek | Buffering is shown; the app stays responsive; playback eventually starts | P2 | Device | Not run
NET-05 | G · Streaming & network | Catalogue unreachable at launch | Supabase blocked | Launch and browse | Home/Search show error or empty states with retry; nothing crashes | P1 | Device | Not run
NET-06 | G · Streaming & network | CDN unreachable | R2 host blocked | Play a track | A clear failure path; no silent endless spinner | P2 | Either | Not run
NET-07 | G · Streaming & network | Local playback server failure | Local server cannot bind | Launch and try to play | The failure is visible and diagnosable; no crash | P2 | Either | Not run
NET-08 | G · Streaming & network | VPN or proxy active | VPN on | Launch and play | Behaviour matches the normal path or fails with a clear message | P3 | Device | Not run
NET-09 | G · Streaming & network | 30-minute session stability | Playing continuously | Play for 30 minutes, switching tracks | Memory stable; no leaks evident; no ANR | P1 | Device | Not run
NET-10 | G · Streaming & network | Image cache is used, not refetched | Device with a warm image cache | Browse Home repeatedly | No image refetch storm; the configured cache is used | P3 | Either | Not run
PRM-01 | H · Premium & paywall (Superwall) | Paywall presents the plans | Signed in, free plan | Tap a paid track | Paywall shows the configured monthly and yearly plans with prices | P0 | Device | Not run
PRM-02 | H · Premium & paywall (Superwall) | Monthly purchase unlocks paid tracks | Paywall open | Complete the monthly purchase | Entitlement becomes active; the tapped track plays; the profile plan label updates | P0 | Device | Not run
PRM-03 | H · Premium & paywall (Superwall) | Yearly purchase unlocks paid tracks | Paywall open on a second account | Complete the yearly purchase | Same as monthly | P1 | Device | Not run
PRM-04 | H · Premium & paywall (Superwall) | Dismissing the paywall | Paywall open | Close without purchasing | No playback, no charge, no entitlement change | P0 | Device | Not run
PRM-05 | H · Premium & paywall (Superwall) | Restore after reinstall | Active subscription, app reinstalled | Sign in again | Entitlement is restored; paid tracks play without a paywall | P0 | Device | Not run
PRM-06 | H · Premium & paywall (Superwall) | Entitlement expiry | Subscription cancelled or expired | Reload the app and tap a paid track | Paid tracks lock again and the paywall returns | P1 | Device | Not run
PRM-07 | H · Premium & paywall (Superwall) | Paywall cannot be presented | No campaign or billing unavailable | Tap a paid track | A Plans are not available yet dialog is shown; the track is NOT granted | P0 | Device | Not run
PRM-08 | H · Premium & paywall (Superwall) | Returning subscriber sees no spurious paywall | Active subscriber, just signed in | Tap a paid track immediately after sign-in | Plays; identity is set before the placement is evaluated | P1 | Device | Not run
PRM-09 | H · Premium & paywall (Superwall) | Upgrade entry point in the profile | Signed in, free plan | Profile; Upgrade to Pro Plan Now | Paywall opens from the profile as well as from a locked track | P2 | Device | Not run
PRM-10 | H · Premium & paywall (Superwall) | Paid state survives restart | Active subscription | Force-stop and relaunch | Paid tracks still play; the profile still shows the paid plan | P1 | Device | Not run
PRM-11 | H · Premium & paywall (Superwall) | Profile plan reflects reality | Free plan, then subscribe, then sign out | Compare the profile row at each step | Free plan / paid plan / signed out are each shown correctly | P2 | Device | Not run
HOM-01 | I · Home | Admin wallpaper band renders | A wallpaper URL is configured | Open Home | The band shows the artwork full-bleed with no broken image and no grey wash | P1 | Device | Not run
HOM-02 | I · Home | No wallpaper configured | Wallpaper empty in the admin | Open Home | Header falls back cleanly to the page surface; no empty band and no error | P2 | Device | Not run
HOM-03 | I · Home | Banner carousel | Specials exist | Swipe the carousel; tap Play Now | Slides are distinct, dots track the page, Play Now starts that shelf (after the sign-in gate when signed out) | P1 | Device | Not run
HOM-04 | I · Home | Featured playlist chips (deity shelves) | featured_playlists rows exist | Tap a chip | Opens that deity shelf; the artwork is the admin-uploaded icon, never blank | P1 | Device | Not run
HOM-05 | I · Home | Every shelf renders and scrolls | Catalogue has content | Scroll Home to the bottom | Albums, tracks, language and recent shelves all render; the last row clears the mini player | P0 | Device | Not run
HOM-06 | I · Home | See-all from a shelf | A shelf has more items than shown | Tap the section arrow or See more card | The full list opens; back returns to Home at the same scroll offset | P1 | Device | Not run
HOM-07 | I · Home | Admin card colours apply | A track and an album have configured colours | Look at the card and the mini player | Card background/text and the mini player colour follow the admin values in both themes | P2 | Device | Not run
HOM-08 | I · Home | Recently played uses live catalogue data | History exists and a cover changed | Open the Recently Played shelf | Current cover and admin colours are shown, not the stale history snapshot | P2 | Device | Not run
HOM-09 | I · Home | Horizontal shelves are smooth | A full catalogue | Fling each shelf quickly | No jank or blank cells; images resolve progressively | P2 | Device | Not run
HOM-10 | I · Home | Empty catalogue | No content reachable | Open Home | Empty states are shown rather than a crash or an endless skeleton | P2 | Device | Not run
SRC-01 | J · Search | Query returns results | Catalogue reachable | Type a title that exists | Matching tracks, artists and playlists appear without typing the full word | P0 | Device | Not run
SRC-02 | J · Search | Tabs filter correctly | Results exist | Switch All / Tracks / Artists / Playlists | Each tab shows the matching subset; counts stay consistent | P1 | Device | Not run
SRC-03 | J · Search | No results | A nonsense query | Search for text that cannot match | A clear empty state; no error surface | P1 | Device | Not run
SRC-04 | J · Search | Play from search results | Signed in | Tap a track in the results | Plays; the queue and mini player are correct | P0 | Device | Not run
SRC-05 | J · Search | See more pagination | A query with many matches | Scroll to the end of a tab | More results load; no duplicates and no infinite spinner | P2 | Device | Not run
SRC-06 | J · Search | Search offline | Airplane mode | Type a query | A clear error or empty state with retry; no crash | P1 | Device | Not run
SRC-07 | J · Search | Non-Latin queries | Telugu/Sanskrit content | Search in Telugu and in transliteration | Both forms find the expected tracks | P1 | Device | Not run
SRC-08 | J · Search | Keyboard and dismissal | Search focused | Submit a query; dismiss the keyboard | The keyboard does not cover results permanently; the query stays | P2 | Device | Not run
LIB-01 | K · Library | Like and unlike a track | Signed in | Tap the heart on a track row twice | Liked Songs updates both times and survives restart | P0 | Device | Not run
LIB-02 | K · Library | Create a playlist | Signed in | Library; New Playlist; name it | The playlist appears immediately and after restart | P0 | Device | Not run
LIB-03 | K · Library | Rename a playlist | A user playlist | Open it; rename | New name shows in Library and on the card | P1 | Device | Not run
LIB-04 | K · Library | Add and remove songs | A user playlist | Add two tracks; remove one | Membership and counts update; the play order is sane | P0 | Device | Not run
LIB-05 | K · Library | Delete a playlist | A user playlist with songs | Delete it and confirm | It disappears from Library; its rows are removed; nothing else is deleted | P0 | Device | Not run
LIB-06 | K · Library | Play a user playlist | A playlist with songs | Use the card play control | Plays in order; the queue shows the playlist | P1 | Device | Not run
LIB-07 | K · Library | Empty library states | A new account | Open Library and its tabs | Friendly empty states; no crash and no broken grid | P2 | Device | Not run
LIB-08 | K · Library | Artist list | History or library artists exist | Open the Artists tab | Artists open their pages and play correctly | P2 | Device | Not run
LIB-09 | K · Library | Server write failure | Network blocked mid-action | Like a track while offline | A clear failure, no phantom local state, no crash | P2 | Device | Not run
PAG-01 | L · Content pages | Album page | Any album | Open it from Home | Header, art, songs and actions render; Play starts the album | P0 | Device | Not run
PAG-02 | L · Content pages | Paid album page | A fully paid album | Open it | Every row shows the padlock; play opens the paywall for a free plan user | P0 | Device | Not run
PAG-03 | L · Content pages | Artist page | An artist with content | Open from a link or Search | Top tracks, albums and related sections load; play works | P1 | Device | Not run
PAG-04 | L · Content pages | Playlist page | A featured or user playlist | Open it | Tracks, shuffle and play work; ownership actions appear only where valid | P1 | Device | Not run
PAG-05 | L · Content pages | Track page | Any track | Open from a row chevron | Play control, details and options work; no dead ends | P2 | Device | Not run
PAG-06 | L · Content pages | Track options menu | Any track | Open the three-dot menu | Share, add to playlist, queue, radio, favourite and details all act correctly | P1 | Device | Not run
PAG-07 | L · Content pages | Long titles and album names | Tracks with long names | Open the album and the player | Text wraps or ellipsizes; no overflow stripes | P2 | Device | Not run
PAG-08 | L · Content pages | Queue page | Playing with a queue | Open the queue from the player | Current track highlighted; editing works; closing returns to the player | P2 | Device | Not run
PAG-09 | L · Content pages | Sources page | A track with multiple sources | Open the sources list | Sources are listed and switching one reloads playback sanely | P3 | Device | Not run
LYR-01 | M · Lyrics | Plain lyrics render | A track with plain lyrics | Player; lyrics tab | Full lyrics render with section labels styled, no broken glyphs | P1 | Device | Not run
LYR-02 | M · Lyrics | Synced lyrics follow playback | A track with synced lyrics | Play and watch the highlight | The active line tracks the audio and scrolls itself | P1 | Device | Not run
LYR-03 | M · Lyrics | Multi-language lyrics | A track with English and Hindi variants | Switch language tabs | Each variant is complete; the tab state is remembered | P2 | Device | Not run
LYR-04 | M · Lyrics | No lyrics | A track without lyrics | Open the lyrics tab | A clear empty state; no crash and no endless skeleton | P2 | Device | Not run
LYR-05 | M · Lyrics | Telugu/Sanskrit rendering | Telugu and Devanagari lyrics | Read them on a phone | Glyphs render correctly, with no boxes or clipped matras | P1 | Device | Not run
LYR-06 | M · Lyrics | Zoom and long lyrics | A very long lyric body | Use the zoom controls; scroll | Zoom works; scrolling stays smooth; no overflow | P3 | Device | Not run
LYR-07 | M · Lyrics | Lyric offsets | Synced lyrics that drift | Watch a full verse | The offset setting corrects drift and persists | P3 | Device | Not run
ANA-01 | N · Analytics / Insights | Header renders | Any state | Open Insights from the bottom bar | Wallpaper band (or the collapsed header without one), title and subtitle render | P1 | Device | Not run
ANA-02 | N · Analytics / Insights | Range selector | History exists | Switch 7 Days, 30 Days, All time | The selected pill moves and the period-scoped numbers change with it | P0 | Device | Not run
ANA-03 | N · Analytics / Insights | Listening Time and Songs Played | History exists | Compare against the Minutes and the Streams pages | The cards agree with the detail pages for the same range | P1 | Device | Not run
ANA-04 | N · Analytics / Insights | Bhakti Streak and Best | A streak of known length | Read the card | Current streak ends today or yesterday correctly; Best is the longest run ever | P1 | Device | Not run
ANA-05 | N · Analytics / Insights | Devotional Days | Plays on known days | Read the card | X of N days matches the days that actually have a play in the range | P1 | Device | Not run
ANA-06 | N · Analytics / Insights | Listening Activity chart | Minutes on known days | Read the bars and their labels | Each bar height matches minutes/axis, the label sits directly above its bar, and the bars sum to the printed week total | P1 | Device | Not run
ANA-07 | N · Analytics / Insights | Chart axis alignment | Any state | Look at the 0/30/60 ticks and the grid lines | Ticks line up with the grid lines, and 0 sits on the baseline | P2 | Device | Not run
ANA-08 | N · Analytics / Insights | Streak day dots | Known play days this week | Read the dot row | Ticked exactly on the days with a play; outlined otherwise | P2 | Device | Not run
ANA-09 | N · Analytics / Insights | Favourite Deity appears with tagged history | Plays on tracks inside a deity shelf | Read the card | The deity with the most minutes is shown, the percentage is of total listening, and the circle shows the admin icon | P1 | Device | Not run
ANA-10 | N · Analytics / Insights | Favourite Deity hidden without matching plays | No plays, or none in a deity shelf | Read the section | The card is absent; only the streak card is shown; no placeholder deity | P1 | Device | Not run
ANA-11 | N · Analytics / Insights | Top Tracks card | History exists | Read the card; tap See all and a row | Three most-played rows with real counts and minutes; See all opens Streams; a row opens the track | P1 | Device | Not run
ANA-12 | N · Analytics / Insights | Card destinations | History exists | Tap Listening Time, Songs Played, the deity card | Minutes, Streams and Playlists open respectively; back returns to Insights | P2 | Device | Not run
ANA-13 | N · Analytics / Insights | Empty history | A fresh, never-played account | Open Insights | All zeros, seven empty bars, no deity card and no Top Tracks card; no crash | P0 | Device | Not run
ANA-14 | N · Analytics / Insights | Numbers match the raw history | A single play of a known length | Compare the card with that track duration | Minutes include exactly that track length, on the right calendar day | P1 | Either | Not run
ANA-15 | N · Analytics / Insights | Dark mode and narrow width | 320dp phone, dark theme | Open Insights | Cards stay legible, no overflow, no clipped captions | P2 | Either | Not run
SET-01 | O · Settings | Theme light, dark, system | Any state | Settings; Appearance; switch themes | Every screen follows the theme immediately and survives restart | P1 | Device | Not run
SET-02 | O · Settings | Colour scheme picker | Any state | Pick several accent schemes | Applied app-wide and persisted; no unreadable combinations | P2 | Device | Not run
SET-03 | O · Settings | Language and region | Any state | Switch to another locale and back | All screens relabel; no missing-string crashes; playback unaffected | P1 | Device | Not run
SET-04 | O · Settings | Playback preferences persist | Any state | Toggle the playback options; restart | Every toggle is remembered and honoured | P2 | Device | Not run
SET-05 | O · Settings | Analytics opt-in is OFF by default | Fresh install | Open Settings; Privacy | The toggle is off; no events are queued or sent before consent | P0 | Either | Not run
SET-06 | O · Settings | Analytics opt-in actually sends | Toggle on | Use the app for a minute; check the PostHog project | Events arrive only after opting in; turning it off stops them and resets identity | P1 | Either | Not run
SET-07 | O · Settings | About screen version | Any build | Settings; About | Shows buildNumber (version) that matches the installed artifact exactly | P1 | Device | Not run
SET-08 | O · Settings | Update check | A newer build published | Open Settings with update checking on | The update prompt appears and its link resolves; dismissing it is safe | P2 | Device | Not run
SET-09 | O · Settings | Restore defaults | Customised settings | Settings; Restore defaults; confirm | Settings reset as described and the app stays usable | P3 | Device | Not run
SET-10 | O · Settings | Logs viewer | Any state | Settings; Logs | Recent logs are listed and copyable; no secrets or tokens appear in them | P3 | Device | Not run
PSH-01 | P · Notifications & push | Push delivered to a signed-in device | Signed in, permission granted | Send a push from the OneSignal dashboard | The notification arrives with the right icon, title and colour | P1 | Device | Not run
PSH-02 | P · Notifications & push | Notification tap deep-links | A push carrying a deeplink | Tap it from the notification shade and from cold start | The app opens the intended screen both ways | P1 | Device | Not run
PSH-03 | P · Notifications & push | Deep link with no payload | A plain push | Tap it | The app just opens; no blank or broken route | P2 | Device | Not run
PSH-04 | P · Notifications & push | In-app message displays | A message scheduled for app_open | Open the app | The message displays once and is dismissible | P2 | Device | Not run
PSH-05 | P · Notifications & push | Permission denied is respected | Permission denied | Sign in and use the app | No repeated prompts; the profile offers Enable Notifications | P2 | Device | Not run
PSH-06 | P · Notifications & push | Push to a signed-out device | Signed out | Send a device-scoped push | It arrives; tapping does not crash | P3 | Device | Not run
LNK-01 | Q · Links & sharing | Share a track | Any track | Track options; Share | The native sheet opens with a sensible title and link | P2 | Device | Not run
LNK-02 | Q · Links & sharing | Open an incoming link | A supported app/deep link | Open it from another app | The right screen opens; back navigation is sane | P2 | Device | Not run
LNK-03 | Q · Links & sharing | Malformed link | A broken or hostile link | Open it | The app stays on a safe screen; no crash and no arbitrary route | P1 | Either | Not run
LNK-04 | Q · Links & sharing | Link to a paid track while signed out | A link to a paid track | Open it signed out | The sign-in gate applies before any playback or paywall | P2 | Device | Not run
CON-01 | R · Connect / remote | Enable Connect | Settings; Connect off | Enable it | A URL/QR is shown and the device becomes discoverable | P2 | Device | Not run
CON-02 | R · Connect / remote | Remote control works | Connect enabled, second client | Play, pause and skip from the client | The phone follows each command and its UI updates | P2 | Device | Not run
CON-03 | R · Connect / remote | Unknown client approval | Connect enabled | Connect from a new client | An approval prompt is shown and denying it blocks the client | P2 | Device | Not run
CON-04 | R · Connect / remote | Disable Connect closes the surface | Connect enabled with a connected client | Disable it | The websocket route is no longer served; the local server binds to loopback only | P2 | Either | Not run
CON-05 | R · Connect / remote | Device picker when Connect is off | Connect off | Tap a track | No device dialog appears; playback is local and immediate | P1 | Device | Not run
ACC-01 | S · Accessibility & i18n | TalkBack on core flows | TalkBack on | Browse Home, open a track, use the player | Every control is announced with a meaningful label; nothing is unreachable | P1 | Device | Not run
ACC-02 | S · Accessibility & i18n | Font scale 200% | Largest system font | Open Home, cards, the player and Insights | No clipped or overlapping text; tap targets stay reachable | P1 | Device | Not run
ACC-03 | S · Accessibility & i18n | Contrast in both themes | Light and dark | Read secondary text on cards and the mini player | Text meets a readable contrast ratio in both themes | P1 | Device | Not run
ACC-04 | S · Accessibility & i18n | RTL locale layout | Arabic locale | Browse Home, settings and the player | Layout mirrors without broken alignment or clipped icons | P2 | Device | Not run
ACC-05 | S · Accessibility & i18n | All shipped locales load | Each of the supported locales | Cycle through them and open the main screens | No missing-string exception and no empty labels | P1 | Device | Not run
ACC-06 | S · Accessibility & i18n | Long German strings | German locale | Read the Insights cards and settings rows | Wrapped or ellipsized; no overflow stripes | P2 | Either | Not run
ACC-07 | S · Accessibility & i18n | Touch targets | Any screen | Tap icon-only controls | All are at least ~48dp and reachable one-handed | P3 | Device | Not run
CMP-01 | T · Compliance & privacy | No Advertising ID in the artifact | Release artifact | CI permission audit | AD_ID absent; the Data safety form says no advertising ID | P0 | CI | Not run
CMP-02 | T · Compliance & privacy | Permission list matches the Data safety answers | Release artifact | Compare the audited permissions with the Play form | Every declared permission is accounted for; no undeclared data collection | P0 | CI | Not run
CMP-03 | T · Compliance & privacy | Privacy policy and account deletion are reachable | Signed in | Settings and Profile | Both are in-app and functional (Play User Data policy) | P0 | Device | Not run
CMP-04 | T · Compliance & privacy | Analytics consent gate | Fresh install | Do nothing for a session | No analytics SDK setup, no distinct id, nothing queued before consent | P0 | Either | Not run
CMP-05 | T · Compliance & privacy | No secrets in the artifact or logs | Release artifact and log dump | Search the APK and logs | No keystore, no service keys, no tokens; the compile-time .env is not shipped as a file | P0 | CI | Not run
CMP-06 | T · Compliance & privacy | Signing key is the Play upload key | Release run | CI keystore SHA pin step | The keystore SHA matches the pinned value; a mismatch fails the build | P0 | CI | Not run
CMP-07 | T · Compliance & privacy | Required .env keys present | Release run | CI required-keys step | SUPABASE_URL, SUPABASE_ANON_KEY, CLERK_PUBLISHABLE_KEY and ONESIGNAL_APP_ID are all non-empty | P0 | CI | Not run
CMP-08 | T · Compliance & privacy | Referral/deep-link attribution consent | Fresh install with a referrer | Launch, sign in | Attribution is bound only after sign-in and never sent without consent | P2 | Either | Not run
PRF-01 | U · Performance & stability | Cold start budget | Mid-range device | Measure 3 cold starts | Consistently under ~3s to the first frame and ~5s to a usable Home | P2 | Device | Not run
PRF-02 | U · Performance & stability | Scroll smoothness | Full catalogue | Fling Home and Search | No sustained jank; images decode without stutter | P2 | Device | Not run
PRF-03 | U · Performance & stability | Memory over a long session | Playing 30 minutes | Watch memory in the profiler | No unbounded growth; no OOM | P1 | Device | Not run
PRF-04 | U · Performance & stability | Battery | Playing 30 minutes, screen off | Compare battery drop with a baseline | No abnormal drain attributable to the app | P3 | Device | Not run
PRF-05 | U · Performance & stability | Monkey stability run | Any build | adb shell monkey -p <pkg> --throttle 300 -v 2000 | No crash and no ANR across 2000 events | P1 | Device | Not run
PRF-06 | U · Performance & stability | Analytics with a large history | 1000+ history rows | Open Insights | Opens within ~2s; scrolling stays smooth | P2 | Device | Not run
PRF-07 | U · Performance & stability | Crash-free rate | Crashlytics | Review after a test cycle | No new fatals; non-fatals triaged | P0 | Either | Not run
REG-01 | V · Regression guards (CI) | Static analysis is not worse than the baseline | Any commit | dart analyze --no-fatal-warnings | Issue count equals the recorded baseline and no errors appear | P0 | CI | Not run
REG-02 | V · Regression guards (CI) | Full unit and probe suite | Any commit | flutter test test | All tests pass (460+ at the time of writing) | P0 | CI | Not run
REG-03 | V · Regression guards (CI) | Drift schema snapshots are valid | Any commit | tool/fix_drift_schema_enums.ps1 then the migration test | The guard passes and the migration suite runs, not skipped | P0 | CI | Not run
REG-04 | V · Regression guards (CI) | Database migrations | Any commit | flutter test test/drift/app_db/migration_test.dart | Every version migrates to the head without data loss | P0 | CI | Not run
REG-05 | V · Regression guards (CI) | Artifact version matches the source | Any build | CI Verify AAB / APK version step | The artifact carries the versionCode derived from pubspec | P0 | CI | Not run
REG-06 | V · Regression guards (CI) | Release APK and AAB both build | Any build | Run the release workflow for apk and appbundle | Both artifacts are produced and signed | P1 | CI | Not run
REG-07 | V · Regression guards (CI) | Secrets are cleaned from the workspace | Any build | CI cleanup step | keystore, key.properties and .env are removed even on failure | P0 | CI | Not run
REG-08 | V · Regression guards (CI) | Playback gate still enforced (source probes) | Any commit | playback_login_gate_test.dart | The gate reads the auth mirror, gates every surface, and the sign-in-before-paywall order holds | P0 | CI | Not run
REG-09 | V · Regression guards (CI) | Analytics derivations correct | Any commit | listening_activity_test.dart and analytics_renditions_test.dart | Windows, streaks, deity attribution and cover renditions are pinned | P1 | CI | Not run
REG-10 | V · Regression guards (CI) | Layout has no overflow at phone widths | Any commit | analytics_layout_test.dart | Cards lay out at 320/360/412dp in both themes | P1 | CI | Not run

## 04 Device matrix
Group | Value | Why it matters | Covered this cycle?
Android version | 8.0 (API 26, minSdk) | Lowest supported OS: media notification, storage, WebView behaviour
Android version | 10 | Scoped storage era; background restrictions
Android version | 12 | Splash-screen API and notification trampoline rules
Android version | 13 | POST_NOTIFICATIONS runtime prompt
Android version | 14 / 15 | Foreground service types and stricter background limits
Android version | 16 (targetSdk 36) | The current target: behaviour changes land here first
Screen width | 320dp | Narrowest phone: card overflow, Insights captions
Screen width | 360dp | Mainstream phone (the device used for this cycle)
Screen width | 411dp / 430dp | Large phones: spacing and carousel counts
Form factor | Tablet 600dp+ | Grid column counts, sidebars, titlebar
Form factor | Foldable / cover screen | Resize without overflow or state loss
System UI | Gesture navigation | Edge swipes vs horizontal shelves
System UI | 3-button navigation | Bottom reserve and SafeArea
Display | Notch / cutout | Status bar overlap on the wallpaper header
Theme | Dark theme | Contrast on tinted cards and the player
Accessibility | Font scale 200% | Text overflow across cards and rows
Performance | Low-RAM device (~2GB) | Image cache pressure, playback stability
Audio | Bluetooth headset | Media buttons and audio focus
Network | Mobile data only | Streaming without Wi-Fi; data usage

## 05 Automated in CI
Guard | What it proves | Where it runs | Manual duplicate needed?
Built commit recorded | The artifact can be traced to the commit it was built from | android-release.yml | No
Signing config written and opened | The keystore and key.properties actually work before a 15-minute compile | android-release.yml | No
Keystore SHA-256 pinned | The build refuses to sign with any key other than the Play upload key | android-release.yml | No
Required .env keys | The build cannot ship with Supabase, Clerk or OneSignal unconfigured | android-release.yml | No
Drift schema guard | Schema snapshots stay compile-valid and the version registry is not empty | android-release.yml | No
Migration test | Every database version migrates to the head | android-release.yml | No
Version resolution | versionName/versionCode come from pubspec, so the About screen cannot disagree with the artifact | android-release.yml | No
Artifact version read back | The produced bundle carries the requested versionCode | android-release.yml | No
AAB signature verified | The bundle is signed with the upload key and will be accepted | android-release.yml | No
Permission audit | AD_ID presence/absence is measured from the artifact, not assumed | android-release.yml | No
Secret cleanup | keystore, key.properties and .env never linger in the workspace | android-release.yml | No
Static analysis | No new analyzer errors and no growth in the issue baseline | flutter-verify.yml | No
Unit + probe suite | 460+ tests: analytics maths, playback gate probes, layout overflow, migrations, caches | flutter-verify.yml | No
Playback gate probes | The gate reads the auth mirror, covers every play surface, and orders sign-in before paywall | flutter-verify.yml | No

## 06 Open items
Item | Why it matters | Action before launch | Owner | Status
Signed-in playback fix (v96) verified only at the stream boundary | The stream endpoint now returns 200 for a signed-in user (was 401), but the on-screen flows were not re-run because the test phone locked mid-verification | Finish rows GAT-09 .. GAT-22 and AUT-10 on a device | QA | Open
Favourite Deity and Top Tracks cards need real history | Both are hidden on an account with no plays, which is correct but leaves them unverified on screen | Play a few typed tracks, then run ANA-09 and ANA-11 | QA | Open
Artists and Albums analytics have no entry point after the redesign | The old summary grid was the only route into the Artists page, and the Top Albums list is no longer reachable | Decide whether they return; if not, remove the dead pages | Product | Open
provider/history/insights.dart buckets days without unixepoch | On drift integer timestamps date(created_at) yields NULL, so that provider errors silently. It is unused by the new screen but still compiled | Delete it with the dead widgets, or fix the SQL to match listening_activity.dart | Eng | Open
Dead stats sections after the Insights rebuild | StatsPageInsightsSection, StatsPageSummarySection, StatsPageTopSection and the donut chart are no longer referenced | Remove them or document why they stay | Eng | Open
Superwall placement paid_track_play must exist as a Gated campaign | Without it every locked track shows Plans are not available yet instead of the paywall | Verify the placement and the monthly/yearly products in the dashboard | Product | Open
Queue actions are not gated while signed out | Add to Queue and Play Next can build a queue that cannot play; pressing play then fails with 401 | Decide policy and cover it in GAT-22 | Product | Open
No download or offline mode | Playback always needs the network; a user expecting offline listening will report it as a bug | Reflect it in the store listing and FAQ, or plan the feature | Product | Open
Paid catalogue is 24 of 79 tracks | Three albums are fully paid; the paywall is reachable only through those | Confirm the split is intended for launch | Product | Open
Test accounts for purchase flows | PRM-02, PRM-05 and PRM-06 cannot be run without a Play licence-test account and a second Google account | Provision both before the gate run | QA | Open
versionCode headroom | 94, 95 and 96 were built during this work; Play rejects anything not above the published one | Confirm the highest published versionCode before bumping | Eng | Open
untranslated_messages.json is generated | It is checked in and drifts when app_en.arb changes | Regenerate with flutter gen-l10n whenever strings change | Eng | Open